## Jira_Backlog
Issue ID | Issue Type | Summary | Description | Story Points | Priority | Assigned To | Branch Name | Status
LT-1 | Epic | English-Hindi Translator Setup | Setup Flask project structure and integrate NLP model | 13 | High | Kunal | feature/project-setup | To Do
LT-2 | Story | UI Design for Translator | Create responsive HTML/CSS interface for text input and output | 5 | Medium | Rahul | feature/ui-design | To Do
LT-3 | Story | Integrate Helsinki NLP Model | Load and configure opus-mt-en-hi model using transformers | 8 | High | Priya | feature/model-integration | To Do
LT-4 | Task | Input Validation | Validate empty and invalid text inputs in Flask | 3 | Medium | Anjali | feature/input-validation | To Do
LT-5 | Story | Deploy to Render | Prepare requirements.txt and Procfile, deploy app to Render | 5 | High | Kunal | feature/deployment-render | To Do
LT-6 | Task | Error Handling | Implement exception handling for model and server errors | 3 | Medium | Rahul | feature/error-handling | To Do
LT-7 | Story | Add Translation API Endpoint | Create REST API endpoint for translation requests | 8 | Medium | Priya | feature/api-endpoint | To Do
LT-8 | Task | Testing and Bug Fixes | Unit testing and resolve identified bugs | 5 | Medium | Anjali | feature/testing | To Do